## 00. Site Report
Project: | [6 empty] | Date: | 2026-05-31
DAILY SITE REPORT | [7 empty] | Rain
[8 empty] | From | To
[7 empty] | 1 | 14:30 | 15:30
Item | Description |  |  | Labor Employed
No. |  |  |  | Carpenter | Fitter | Helper | Mason | Skilled | Unskilled
Total
Today's Total Strength
Remarks (Shortfall of Labors/ Materials, if Any) |  |  |  | RMC Report (All Grades) |  |  | Reinforcement Steel Report
|  |  |  | Description |  | Quantity | Description |  | Quantity
|  |  |  | Previous Receipt |  |  | Previous Receipt
|  |  |  | Today's Receipt |  |  | Today's Receipt
|  |  |  | Cumulative Receipt |  |  | Cumulative Receipt
|  |  |  | Opening Blanace |  |  | Opening Blanace
|  |  |  | Today's Consumption |  |  | Today's Consumption
|  |  |  | Closing Balance |  |  | Closing Balance
Decisions Pending/ Required (Client/ Consultants/ HO)
Milestones Achived/ Missed
Material Receipt Report
Item | Material Description | Unit | Supplier Details |  |  |  | Material Received
No. |  |  | Name |  |  | Challan No | Previous | Toady | Cum.
Site Visitors
[5 empty] | Prepared By |  |  | Site Incharge

## 1.01 Weather
Date: | Temp @ 12PM | Rain Start | Rain Start2 | Remarks
2026-05-31 | 36 | 14:30 | 15:30
2026-05-31 | 36 | 17:30 | 18:15

## 1.02 Site Diary
SITE DIARY
Sr. No. | Date | Details | Remarks

## 1.03 Hindrance
HINDRANCE REGISTER
Sr. No. (1) | Date (2) | Details of Hindrance (3) | Items of work that are affected due to the Hindrance (4) | Date of Recording (5) | Start Date of Hindrance (6) | Date of Closure of Hindrance (7) | Total Period of Hindrance (8 = 7 - 6) | Overlapping Period/ Float, if any (9) | Net hindrance days (10 = 8 - 9) | Approved by | Remarks

## 2.01 Customer Milestones
CUSTOMER MILESTONE
Date: | Customer Milestone | Activity | Proposed Completion Date | Work Completed Today (%age) | Contractor

## 2.02 Construction Milestone
CONSTRUCTION MILESTONE
Date: | Construction Milestone | Activity | Work Completed Today (%age) | Contractor

## 2.03 Work & Labor
WORK COMPLETION AND LABOR DETAILS
Date: | Milestone | Activity | Work Completed | Unit | Contractor | Category | No. of Labors | Remarks

## 2.04 Dept. Lab Register
Departmental Labour Register
Sr. No. | Date | Challan No. | Sub-Contractor's Name | Name of the Labor | Labour Category | No. of Mandays | Workdone Details | Approx. Quantity | Unit | Recovery From | Recovery Rate | Recovery Amount | Authorised by | Debit Details | Cost Head | Remarks

## 3.01 Material Recpt
MATERIAL RECEIPT
Sr. No. | Date | Time in | PO No. | GRN No | Material Description | Unit | Supplier | Quantity Received | Quantity Rejected | Quantity Accepted | Remarks

## 3.02 Mat Issue Reg
Material Issue Register
Sr. No. | Date | Time | Issue Slip No | Issue Slip Date | WO No | CONTRACTOR NAME | GRN No. | MATERIAL NAME | UNIT | QTY ISSUED | QTY Returned | Net Qty Issued | Construction Milestone | WBS 1 | WBS 2 | Cost Head | LOCATION | Remarks

## 3.03 PR
Purchase Requisition
Sr. No. | PR No. | Cost Head | Construction Milestone | WBS 1 | WBS 2 | Item Specification | Unit | Required Quantity | Budget Rate | Budget Amount | Required Date | Remarks

## 3.04 PO
Purchase Order
Sr. No. | PR No. | PO No. | PO Date | Item Specification | Unit | PO Quantity | PO Rate | PO Amount | Remarks

## 3.05 RMC
Purchase Requisition
Sr. No. | PR No. | Construction Milestone | WBS 1 | WBS 2 | Location | Grade of Concrete | Unit | Quantity Received | Quantity Rejected | Quantity Accepted | Cube Markings | Remarks

## 3.06 Reinf
Reinforcement Steel Receipt Register
Sr. No. | Date | PO No. | GRN No | Supplier | Steel Specifications | Steel Dia | Total Length Received | Total Weight | Quantity Accepted | Remarks

## 3.07 WO Reg
Sr. No. | Cost Head | Dept | WO No | Date | Name of the Agency | Quotation Ref & Date | PAN | GST No. | Work Order Details | Work Order Value (Excl Taxes) | GST on WO | Work Order Value (Incl Taxes) | Allocated Budget | Diff in Budget - WO Value | Remarks
1

## 3.08 Con Invoice Reg
Sr. No. | Contractor | WO No | Invoice No. | Invoice Date | Invoice Status | Gross Claimed Amount | Gross Certified Amount | GST | Retention | Debits | TDS | Net Payable | Payment Due on | Payment Method | Payment Instrument Details | Net Amount Paid | Date of Payment | Remarks | Received on | Ch. Amount | Ch. No. | Remarks

## 3.09 Mat Invoice Reg
Sr. No. | Supplier | PO No | Invoice No. | GRN Nos. | Invoice Date | Invoice Status | Gross Claimed Amount | Gross Certified Amount | GST | Debits | Net Payable | Payment Due on | Payment Method | Payment Instrument Details | Net Amount Paid | Date of Payment | Remarks

## 4.01 Machinery Log
Machinery Logbook
Sr. No. | Date | Challan No. | Machinery Name | Sub-Contractor's Name | Fuel/ Other Cost by Client | Time Start | Time Finish | Total Hours | Rate | Amount | Cost Head | Workdone Details | Milestone | WBS 1 | WBS 2 | Approx. Quantity | Unit | Recovery From | Recovery Rate | Recovery Amount | Authorised by | Debit Details | Remarks

## 5.01 Dwg Reg
DRAWING REGISTER
Sr.No. | Building | Type | Particulars | Required Date | DWG No. | DWG Date | Rev | Rev Date | Recd Date | Status/ Remarks
1 |  | Data | Contour Plan
2 |  | Data | Excavation Plan
3 |  | Data | Bore log Details for strata classification
4 |  | Data | Basement Floor Plan ( Lower Level Parking)
5 |  | ARCHITECTURAL | Ground Floor Plan ( Upper Level Parking )
6 |  | ARCHITECTURAL | 1st Floor Plan/ Podium Floor Details
7 |  | ARCHITECTURAL | Odd Floor Plans
8 |  | ARCHITECTURAL | Refuge Floor Plans
9 |  | ARCHITECTURAL | Even Floor Plans
10 |  | ARCHITECTURAL | Terrace Floor Plan
11 |  | ARCHITECTURAL | Terrace Waterproofing Details
12 |  | ARCHITECTURAL | Above Terrace,LMR,Staircase Headroom,OHWT etc Floor Plan
13 |  | ARCHITECTURAL | Dry Balcony, Att.Terrace & Staircase Railing
14 |  | ARCHITECTURAL | Entrance Lobby Details ( Flooring ,Wall & Ceiling )
15 |  | ARCHITECTURAL | Typical Floor Lobby Details ( Flooring ,Wall & Ceiling )
16 |  | ARCHITECTURAL | Flat & Common Passage Flooring Layout as per Tiles Specifications
17 |  | ARCHITECTURAL | Doors & Windows Detailed specification and Dwg.
18 |  | ARCHITECTURAL | Doors & Windows Fixing Details
19 |  | ARCHITECTURAL | Window Grills Fixing Details
20 |  | ARCHITECTURAL | Flat & Common Passage False Ceiling Layout
21 |  | ARCHITECTURAL | Kitchen Otta Details
22 |  | ARCHITECTURAL | Att Terraces, Dry Balcony & Toilets layout
23 |  | ARCHITECTURAL | Toilets Dado -Wall Elevation
24 |  | ARCHITECTURAL | Details for Typical Toilet
25 |  | ARCHITECTURAL | Details for Typical Dry Balcony
26 |  | ARCHITECTURAL | Details for Typical Attached Terrace
27 |  | ARCHITECTURAL | Elevation-A Side
28 |  | ARCHITECTURAL | Elevation-B Side
29 |  | ARCHITECTURAL | Elevation-C Side
30 |  | ARCHITECTURAL | Elevation-D Side
31 |  | ARCHITECTURAL | Elevation Treatment Details
32 |  | ARCHITECTURAL | Elevation Arctitectural Projection/ Boxes/ Pins Details
1 |  | ARCHITECTURAL | Working Section & Details -01
2 |  | ARCHITECTURAL | Working Section & Details -02
3 |  | ARCHITECTURAL | Working Section & Details -03
4 |  | ARCHITECTURAL | Working Section & Details -04
5 |  | ARCHITECTURAL | Section Through Toilet Sunk
6 |  | ARCHITECTURAL | Section Through Terraces Sunk
7 |  | ARCHITECTURAL | Section Through Staircase
1 |  | STRUCTRAL | Footings Layout,Sections & Details
2 |  | STRUCTRAL | Combined Footings Sections & Details
3 |  | STRUCTRAL | Lift Raft & RCC Walls Sections & Details
1 |  | STRUCTRAL | Columns Layout & Schedule, Links Details
2 |  | STRUCTRAL | Shear Wall Layout, Section,Schedule & Link Details
1 |  | STRUCTRAL | Basement Floor-Raft Slab
2 |  | STRUCTRAL | Tie Beams Framing & Beams Schedule
3 |  | STRUCTRAL | Plinth Beams Framing & Beams Schedule
4 |  | STRUCTRAL | Upper Floor Parking -1st Slab
5 |  | STRUCTRAL | 1st Floor
6 |  | STRUCTRAL | Typical Odd Floor Slab
7 |  | STRUCTRAL | Typical Even Floor Slab
8 |  | STRUCTRAL | Refuge Floor Slab
9 |  | STRUCTRAL | Terrace Floor Slab
10 |  | STRUCTRAL | LMR Bottom & Top Slab
11 |  | STRUCTRAL | OHWT Bottom & Top
12 |  | STRUCTRAL | OHWT RCC Pardhi Section & Details
13 |  | STRUCTRAL | Staircase Section & Details
14 |  | STRUCTRAL | Pergola Details
1 |  | STRUCTRAL | Basement Floor- GF Slab
2 |  | STRUCTRAL | UGWT
3 |  | STRUCTRAL | Ramp Details
1 |  | Plumbing | Basement Floor Plan ( Drainage & Strom water ,Sump Well Details)
2 |  | Plumbing | Basement Floor Plan (Sump Well Details)
3 |  | Plumbing | Ground Floor Plan ( Layout for Drainage,Strom water & Water supply)
4 |  | Plumbing | Upper Floor Plan ( Layout for Drainage,Strom water & Water supply)
5 |  | Plumbing | Typical Odd Floor Plan ( Layout for Drainage,Strom water & Water supply)
6 |  | Plumbing | Typical Even Floor Plan ( Layout for Drainage,Strom water & Water supply)
7 |  | Plumbing | Toilet Layout ( Wall Elevation, Drainge & Water supply Lines Details)
8 |  | Plumbing | Duct Layout ( Vertical Drainage & Water Supply Down Take Lines Details)
9 |  | Plumbing | Terrace Layout ( Rising Main & Ring Main for water supply )
10 |  | Plumbing | OHWT ( Lauout,Section & Plumbing Details )
11 |  | Plumbing | UGWT Layout & Section Details
12 |  | Plumbing | UGWT Pump Room & Sump Details
13 |  | Plumbing | UGWT Inlet & Outlet Plumbing Details
14 |  | Plumbing | STP Input & Output Plumbing Detials
15 |  | Plumbing | Typical Detials of Toilet
16 |  | Plumbing | Typical Detials of Dry Balcony
17 |  | Plumbing | Typical Detials of Att.Terrace
18 |  | Plumbing | Typical Detials of Kitchne
1 |  | Electrical | Basement Floor Plan
2 |  | Electrical | Ground Floor Plan
3 |  | Electrical | Typical Odd Floor Plan
4 |  | Electrical | Typical Even Floor Plan
5 |  | Electrical | Typical Flat Layout
6 |  | Electrical | Common area Layout Plan
7 |  | Electrical | Entrance Lobby Layout
8 |  | Electrical | Meter Room Details
9 |  | Electrical | Data Cable /Telephone /Intecom Layout
10 |  | Electrical | Elect Shaft Details
11 |  | Electrical | External Electrical layout
1 |  | Fire Fighting | Basement Floor Plan ( Lower Lavel Parking)
2 |  | Fire Fighting | Ground Floor Plan ( Upper Level Parking)
3 |  | Fire Fighting | Down take Layout
4 |  | Fire Fighting | Common area Layout Plan
5 |  | Fire Fighting | Sprinkler System for Basement Layout
6 |  | Fire Fighting | Sprinkler System for Floor & Inside Flats
7 |  | Fire Fighting | Fire Hydrant Layout
8 |  | Fire Fighting | Pressurisation Shaft Details ( HVAC)
9 |  | Fire Fighting | Pump Room Details
1 |  | Mechanical | Basement Floor Plan ( Lower Lavel Parking)
2 |  | Mechanical | Ground Floor Plan ( Upper Level Parking)
3 |  | Mechanical | Stack Parking Pit Details

## 5.02 RFI Reg
RFI LOG
RFI NO | Consultant | Trade | RFI Date | Send By | Drawing Reference | RFI Details | References | Urgency | RESPONSIBLE | Target Date | STATUS | REMARKS

## 5.03 Instruction Reg
Site Instructions Log
Date | Time | Consultant/ Instructor | Details of Instructions | Impact on Time (Y/ N) | Impact on Cost (Y/ N) | Documentation Done (Y/N) | Documentation Details (Mail, Drawing etc.) | Authourized by | Date of Authourization | Remarks

## 6.01 WaterTank
Water Tankers Supply Register
Date | Time | Supplier | Challan No. | Vehilcle No | Volume in Ltr (Drinking) | Volume in Ltr (Domestic) | Remarks

## 6.02 Ele Meter
Weekly Electricity Usage Register
Meter No. | Reading Date | Reading Time | Reading | MSEB Bill Date | MSEB Bill Amount | Payment Date | Payment Amount | Remarks

## 6.03 Petty Cash
Petty Cash Register
Sr. No. | Cost Head | Date | Expenses Details | Amount Received | Paid to | Amount Paid | Debit to | Debit Details | Remarks

## 7.01 Plan Board
Plan Board
Sr. No. | Construction Milestone | WBS 1 | WBS 2 | Activity | Location | Cost Head | Resource | Unit | Quantity | Rate | Unit | Amount | Expected Date of Start | Expected Date of Completion | Remarks

## 8.01 CubeTest
Cube Test Register
Sr. No. | Date of Casting | Grade of Concrete | Brand/ Grade of Cement | Structure & Location of which the cube has been taken | Cube Marking | Date of 7 days test | Date of 28 days test | Wt. of Cube | Load (KN) | Compressive Strength (N/mm2) | Avg. Compressive Strength (N/mm2) | Sign | Remarks

## 8.02 QC
Quality Non Confirmity Register
Sr. No. | NC No | Date | SubContractor's Name | Activity | NC Description | Suggested Remedy | Responsible Person | NC Closure Details | Closure Date | Closure Authorised by | Remarks